IASFAA Program Committee Calendar

July - Submit IASFAA Committee Annual Budget Proposal Form to the VP by the end of the month or deadline set during Executive Council Summer Retreat (LINK) - Create calendar for the upcoming year, submit to President by due date set during Executive Council Retreat - Make sure co-chair has access to google folder

August - Committee meeting - Decide on conference theme, slogan if any - Assign tasks (see planning spreadsheet) - Decide on meeting time/date, set all zoom appointments - Discuss session proposals, come up with additional topic areas if needed - Set up in-person site visit at conference site, coordinate with site committee - Attend Executive Council bi-monthly zoom meeting

September - Committee meeting - Discuss survey result takeaways - Submit NASFAA speaker request form - Meet with Site committee to go over food/room costs vs revenue; submit to VP - Send call for sessions proposals

October - Committee meeting - Send reminder to collect sessions proposals ahead of in-person meeting - Finalize agenda

November - In-person planning meeting at conference hotel - Brainstorm charity ideas - Brainstorm entertainment ideas - Hold weekly zoom meetings (approx 30 minutes depending on unfinished tasks) - Advertise conference (collab with Communication) - Obtain travel plans from special guests

December - PowerPoint template out to presenters - Select keynote speaker(s) - Schedule registration testing with Electronic Services - Set registration for mid-to-late January or early February - Finalize session topics - Finalize presenters/special guests and collect bios - Request for presenters if needed

January - Committee meeting - Schedule meeting with Site to go over food costs/registration costs - Continue working through program-related tasks (see spreadsheet) - Early bird registration opens

February - Committee meeting - Early bird registration closes - Regular registration opens - Collect session titles and descriptions for program - Hotel block - advertise

March - Committee meeting - Menus due - Remind presenters to turn in PPT to Site (for uploading to conference computer) & Electronic Services (for uploading to the website) - Due: month before conference - Finalize program and confirm logos with Exhibitor Relations

April - Registration closes - Develop conference schedule for President - Spring Conference - Attend Executive Council In-Person meeting during conference - Post-conference - Send survey to conference attendees within week of conference - Close survey after two weeks - Compile survey results and share with co-chair for discussion at next year’s in-person program meeting - Develop list of all conference costs and breakdowns of attendees. Co-char may need this for Executive Council Summer Retreat and/or to provide to finance committee for closing of the books - Review all bills with Site and reconcile all program statements and billings (do this with co-chair as well)

May - Attend Executive Council bi-monthly zoom meeting - Prepare end-of-year report for upcoming Executive Council Summer Retreat

June - Co-chair attends Executive Council Summer Retreat as Chair for 2026-27